## Sheet1
Week |  | Release #
2020-07-14 | Connect to Azure Cloud and GITHUB
2020-07-21 | Enable GitHub actions | 1.1
2020-07-28 | Local testing
2020-08-04 | Enable GitHub and the Azure pipelines | 2.1
2020-08-11 | Verify remote tests pass
2020-08-18 | Bug fixing and documentation and project submission | 1.2
Top 3 Quarter Goals | Order Prioritized Features | Proposed Difficulty 1-3 (1 easy and 3 is tough) | Feature Category | Project Management Guidelines
Connect Azure to Github | create a Github repo | 1 | Create a github repo and connect to Azure | Demo every monday
Do continuous Integration | set up Azure shell | 2 | Use Azure Cloud shell to make the files | Weekly planning after demo
DO continuous Delivery | deploy using Azure pipeline | 3 | Use an appservice to deploy a pipeline for continuous delivery | Consumer/Stakeholder Release every 2 weeks
Tickets represents 4 hour - 7 day block of work